## ASpace 2017
ArchivesSpace Technology and Development Roadmap*
Categories of Work | Pending Work | Minor Release: 1.5.3 Feb 2017 | Major Release: 1.6 March 2017 | Minor Release: 1.6.1 April 2017 | Minor Release: 1.6.2 May 2017 | Major Release: 1.7 June 2017 | Minor Release: 1.7.1 June 2017 as necessary | Minor Release: 1.7.2 Aug 2017 as necessary | Major Release: 1.8 Oct 2017 | Developed/Funded by
Major Feature Enhancements/Functionality (potential)
Work with community to determine priorities for major enhancements once time estimates available
| PUI |  | PUI Beta Release |  |  | PUI |  |  |  | This a separate stream of development work; largely funded/managed by Yale & Harvard; included here for continuity
| Reports refactoring |  | Initial refactoring of reports
| Rights Management |  |  |  |  | Rights management?
| OAI-PMH | [7 empty] | TBD
EAC-CPF (Agents refactoring)
EAD3 support
Repair/Refactor
| Improve performance of resource trees with thousands of sibling components |  | improved resource tree performance
| Reports - remove Jasper; ensure the current reports function correctly and that the UI for selecting, parameterizing and running reports is usable |  | Reports - ensure current reports function correctly
| Background jobs - improved UI and queueing |  | Background jobs
| Rails 5 (before PUI can be merged) and Jruby upgrades |  | Rails 5 and Jruby upgrades
| Tests - ongoing efforts to make automated testing more reliable, improve coverage and roustness |  | improved tests |  |  | improved tests
Areas Which May Be Complete for March
| PUI merge - incorporate new PUI app into core codebase, merge changes into ASpace core |  | PUI merge components |  |  | any PUI component merge not completed earlier
| Indexer - refactor to improve reliability, performance and maintainability |  | Indexer |  |  | Indexer (if not completed earlier)
| Container Management - remove old container model and rework imports, exports, reports, etc to use the new container model; detailed requirements tbd. Will likely need a community group to help in developing these |  | start container management work |  |  | complete container management merge
| smaller items | small items as time permits | small items as time permits | small items as time permits | small items as time permits | small items as time permits | small items as time permits | small items as time permits | small items as time permits
Review resequencing
Improve API auto-documenation
Consider removing /docs from the core code repository
Investigate alternatives to Puma
Ensure external Solr implementations work reliably
| "search for nothing stories" |  | "search for nothing stories" | [6 empty] | Yale
Bug Fixes
| 1620; 1619; 1373, 1562; Prioritization committee to prioritize additional bugs; HM will work from prioritized list; it will generally occur in prioritized order but difficulty and adjacency may impact order | bug fixes - more details as release date approaches | bug fixes - more details as release date approaches | bug fixes - more details as available | bug fixes - more details as available | bug fixes - more details as available | bug fixes - more details as available | bug fixes - more details as available | bug fixes - more details as available
Note - many bugs will be addressed by refactoring work outlined above; they are not individually repeated in this section
Minor Feature Enhancements
Current prioritized ones are: | 1002, 940; 1500, 925, 935, 1057, 996, 1376, 1511, 1513; 1411; Prioritization committee to prioritize additional ones; HM will work from prioritized list; it will generally occur in prioritized order but difficulty and adjacency may impact order |  | feature enhancements - more details as release date approaches |  |  | feature enhancements - more details as available |  |  | feature enhancements - more details as available
prioritization subteam to prioritize JIRA tickets; HM will work from list for each EPIC category below
Staff interface: full list at: https://archivesspace.atlassian.net/browse/AR-1112
Import - full list at: https://archivesspace.atlassian.net/browse/AR-1092
Export - full list at: https://archivesspace.atlassian.net/browse/AR-1093
Migration tools
Note - some minor feature enhancements will be addressed by refactoring work outlined above; they are not individually repeated in this section
*All development timeframes are subject to change depending on work progress. Items are given as benchmarks; the items closer in time are commitments; the farther out in time the roadmap goes, the less specificity is available
**Any changes to the data model or API will be communicated to the integrations sub-team
Please note additional tabs below identify work for each major release

## March 2017
ArchivesSpace Technology and Development Roadmap
Categories of Work | Major Release: 1.6 March 2017
Major Feature Enhancements/Functionality
PUI Beta Release
Initial refactoring of reports
Repair/Refactor
improved resource tree performance
Reports - ensure current reports function correctly
Background jobs
Rails 5 and Jruby upgrades
improved tests
Areas Which May Be Complete for March
PUI merge components
Indexer
small items as time permits
"search for nothing stories"
Bug Fixes
bug fixes - more details as release date approaches
Minor Feature Enhancements
feature enhancements - more details as release date approaches

## June 2017
ArchivesSpace Technology and Development Roadmap
Categories of Work | Major Release: 1.7 June 2017
Major Feature Enhancements/Functionality
PUI
Rights management?
Repair/Refactor
improved tests
any PUI component merge not completed earlier
Indexer (if not completed earlier)
small items as time permits
Bug Fixes
bug fixes - more details as available
Minor Feature Enhancements
feature enhancements - more details as available