## ASpace 2017
ArchivesSpace Technology and Development Roadmap*
Categories of Work | Pending Work |  | Release: 2.0.1 May 2017 | Release: 2.1 June 2017 | Release: 2.2 Sept 2017 | Release: 2.3 early Dec 2017 | Responsibility (Developed/Funded by) | JIRA Ticket
Major Feature Enhancements/Functionality |  | status of requirements
| PUI |  |  | PUI |  |  | largely funded/managed by Yale & Harvard | https://archivesspace.atlassian.net/browse/AR-1113
| Rights Management | complete |  | Rights management |  |  | ASpace - HM | https://archivesspace.atlassian.net/browse/AR-1107
| OAI-PMH | complete |  | OAI-PMH |  |  | ASpace - HM | https://archivesspace.atlassian.net/browse/ANW-49
| EAC-CPF (Agents refactoring) | in process |  |  |  | EAC-CPF (Agents refactoring) | ASpace - HM
| EAD3 support (start with: creating additional export pathway) | in process |  |  | EAD3 support? |  | Seeking community developer/s | https://archivesspace.atlassian.net/browse/AR-923
| Migration tools | need requirements |  |  | Migration tools? |  | ASpace - co-op student?
| Easier deployment for those with limited IT support - create Windows Installer | need requirements |  |  | Windows installer? |  | ASpace - co-op student?
| Assessment module | in process |  |  | Collection Assessment |  | Tufts | https://archivesspace.atlassian.net/browse/AR-819
| Date calculator (similar to extent calculator) | complete |  |  | Date calculator |  | Yale | https://archivesspace.atlassian.net/browse/AR-1733
| LCNAF plugin (enhancements) | under review by community |  |  |  | LCNAF plugin | Yale | https://archivesspace.atlassian.net/browse/AR-1732
| New data map for MARC XML export | in process |  |  |  | data map for MARC XML export | Yale | https://archivesspace.atlassian.net/browse/AR-924
| CSV importer plugin |  |  | beta CSV importer plugin |  |  | Harvard | https://archivesspace.atlassian.net/browse/AR-935
| Integration with other systems, most especially Aeon, Hydra, ArcLight, Islandora, CollectionSpace | timing/needs dependent on other systems
| Digital object module redo | convene targeted working group
| Digital Object exports (MODS, METS, DC) | draft data mapping under review | [5 empty] | https://archivesspace.atlassian.net/browse/AR-921 (Dublin Core)
https://archivesspace.atlassian.net/browse/AR-920 (MODS)
https://archivesspace.atlassian.net/browse/AR-919 (METS)
Future Potential Priorities
Bulk editing and redesign of RDE
| Redesign of staff interface with increased accessibility and ability to do arrangement using the interface (sort in various ways regardless of how data is entered) | working group to be formed
| Support for multi-lingual description | French, Italian underway
External authority database integration, including SNAC, AAF, VIAF
Increased support for describing and managing audiovisual materials
Repair/Refactor
| Reports |  | patches if necessary | additional reports improvements |  |  | ASpace - Laney McGlohon
| Tests - automated testing more reliable, improve coverage and roustness |  |  | testing revamp completed |  |  | ASpace - HM
| Container Management - remove old container model and rework imports, exports, reports, etc. to use the new container model |  |  | container management |  |  | ASpace - HM
| Improve API auto-documentation |  |  | improve API auto-doc |  |  | ASpace - HM
Bug Fixes
| Prioritized by Development Prioritization subteam |  | details as available | details as available | details as available | details as available | ArchivesSpace - HM | https://archivesspace.atlassian.net/issues/?filter=12101
Minor Feature Enhancements
| Prioritized by Development Prioritization subteam: 940, 1500, 925, 935, 1057, 996, 1376, 1511, 1513; 1411 | [5 empty] | Seeking community developer/s | https://archivesspace.atlassian.net/browse/AR-925?filter=12903
| 1002 - insert sibling records below highlighted record |  |  | insert sibling record |  |  | ASpace - HM | https://archivesspace.atlassian.net/projects/AR/issues/AR-1002
*All development timeframes are subject to change depending on work progress. Items given as benchmarks; items closer in time are commitments; the farther out in time the roadmap goes, the less specificity is available
**Any changes to the data model or API will be communicated to the integrations sub-team
Please note additional tabs below identify work for each major release

## June 2017
ArchivesSpace Technology and Development Roadmap
Categories of Work | Release: 2.1 June 2017
Major Feature Enhancements/Functionality
PUI
OAI-PMH
Rights management
CSV importer - beta
Repair/Refactor
improved tests
Container Management
improve API auto-doc
Bug Fixes
bug fixes - details as available
Minor Feature Enhancements
insert sibling records below highlighted record

## Sept 2017
ArchivesSpace Technology and Development Roadmap
Categories of Work | Release: 2.2 Sept 2017
Major Feature Enhancements/Functionality
Collection Assessment
Date calculator
EAD3 support?
Migration tools?
Windows installer?
Repair/Refactor
Bug Fixes
details as available
Minor Feature Enhancements
details as available

## Dec 2017
ArchivesSpace Technology and Development Roadmap
Categories of Work | Release: 2.3 Dec 2017
Major Feature Enhancements/Functionality
EAC-CPF (Agents refactoring)
LCNAF plugin
data map for MARC XML export
Repair/Refactor
Bug Fixes
details as available
Minor Feature Enhancements
details as available