## ASpace 2017
ArchivesSpace Technology and Development Roadmap*
Categories of Work | Pending Work |  | Release: 2.1.1 Aug 2017 | Release: 2.2 Sept 2017 | Release: Dec 2017 | Release: March 2018 | Responsibility (Developed/Funded by) | JIRA Ticket
Major Feature Enhancements/Functionality |  | status of requirements
| PUI |  | PUI enhancements |  |  |  | ASpace - HM | https://archivesspace.atlassian.net/browse/AR-1113
| OAI-PMH |  | OAI-PMH enhancements |  |  |  | ASpace - HM | https://archivesspace.atlassian.net/browse/ANW-49
| EAD3 support (start with: creating additional export pathway) | complete |  | EAD3 support |  |  | NCSU/Duke | https://archivesspace.atlassian.net/browse/AR-923
| Assessment module | complete |  | Collection Assessment |  |  | Tufts | https://archivesspace.atlassian.net/browse/AR-819
| Migration tools | need requirements |  |  | Migration tools |  | ASpace - co-op student
| Easier deployment for those with limited IT support - create Windows Installer | need requirements |  |  | Windows installer |  | ASpace - co-op student
| New data map for MARC XML export | in process |  |  | data map for MARC XML export |  | ASpace & seeking community developers | https://archivesspace.atlassian.net/browse/AR-924
| LCNAF plugin (enhancements) - perhaps part of agents? | complete |  |  | LCNAF plugin? |  | Yale | https://archivesspace.atlassian.net/browse/AR-1732
| External authority database integration, including SNAC, AAF, VIAF | SNAC requirements complete |  |  | SNAC integration? |  | ASpace/SNAC | https://archivesspace.atlassian.net/browse/AR-1864
| EAC-CPF (Agents refactoring) | near completion |  |  |  | EAC-CPF (Agents refactoring)? | ASpace - HM?
| Redesign of staff interface, including better accessibility | working group formed; full recommendations expected early 2018; minor enhancements may be phased in earlier |  |  |  | minor enhancements? |  | https://archivesspace.atlassian.net/browse/AR-1112
| Integration with other systems, most especially Aeon, Hydra, ArcLight, Islandora, CollectionSpace | timing/needs dependent on other systems
| Digital object module redo | convene targeted working group
| Digital Object exports (MODS, METS, DC) | draft data mapping under review | [5 empty] | https://archivesspace.atlassian.net/browse/AR-921 (Dublin Core)
https://archivesspace.atlassian.net/browse/AR-920 (MODS)
https://archivesspace.atlassian.net/browse/AR-919 (METS)
Future Potential Priorities
| Bulk editing and redesign of RDE | part of staff interface working group
Support for multi-lingual description
Increased support for describing and managing audiovisual materials
Container Management - additional features
Repair/Refactor
| Reports |  |  | additional reports improvements | additional reports improvements | additional reports improvements | ASpace - Laney McGlohon | https://archivesspace.atlassian.net/browse/ANW-1
| Tests - automated testing more reliable, improve coverage and roustness |  |  | testing improvements | testing improvements | testing improvements | ASpace - Laney McGlohon
| Automated generation of release notes |  |  | automated generation of release notes |  |  | ASpace - Laney McGlohon
| Improve API auto-documentation |  |  |  | API auto-documentation? |  | ASpace - co-op student
| Data Dictionary |  |  |  | Data Dictionary |  | ASpace - Laney McGlohon
Bug Fixes
| Prioritized by Development Prioritization subteam |  | see release notes | details as available | details as available | details as available | ArchivesSpace | https://archivesspace.atlassian.net/issues/?filter=12101
Minor Feature Enhancements
| Prioritized by Development Prioritization subteam: 925, 935, 940, 1376, 1500, 1511, 1718 | [5 empty] | Seeking community developer/s | https://archivesspace.atlassian.net/browse/AR-925?filter=12903
| staff interface jiras included in staff interface working group enhancement listed above | [6 empty] | https://archivesspace.atlassian.net/browse/AR-1112
*All development timeframes are subject to change depending on work progress. Items given as benchmarks; items closer in time are commitments; the farther out in time the roadmap goes, the less specificity is available
**Any changes to the data model or API will be communicated to the integrations sub-team
Please note additional tabs below identify work for each release

## Aug 2017
ArchivesSpace Technology and Development Roadmap
Categories of Work | Release: 2.1.1 Aug 2017
Major Feature Enhancements/Functionality
PUI enhancements
OAI-PMH enhancements
Repair/Refactor
Bug Fixes
see release notes
Minor Feature Enhancements

## Sept 2017
ArchivesSpace Technology and Development Roadmap
Categories of Work | Release: 2.2 Sept 2017
Major Feature Enhancements/Functionality
EAD3 support
Collection Assessment
Repair/Refactor | additional reports improvements
testing improvements
automated generation of release notes
Bug Fixes
details as available
Minor Feature Enhancements
details as available

## Dec 2017
ArchivesSpace Technology and Development Roadmap
Categories of Work | Release: Dec 2017
Major Feature Enhancements/Functionality | migration tools
Windows installer
data map for MARC XML export
LCNAF plugin?
SNAC integration?
Repair/Refactor | additional reports improvements
testing improvements
API auto-documentation?
Data Dictionary
Bug Fixes | details as available
Minor Feature Enhancements | details as available

## March 2018
ArchivesSpace Technology and Development Roadmap
Categories of Work | Release: March 2018
Major Feature Enhancements/Functionality | EAC-CPF (Agents refactoring)?
minor enhancements?
Repair/Refactor | additional reports improvements
testing improvements
Bug Fixes | details as available
Minor Feature Enhancements | details as available